TASTYBYTES

Restaurant Management System

Stage 1  —  Feasibility Study

| Document Type | Feasibility Study — All Five Types |
| --- | --- |
| Project | TastyBytes — Shiva Dhaba Restaurant System |
| Client | Ramesh Gupta, Owner — Shiva Dhaba, Ghaziabad |
| Prepared By | Aakash Jangid, Software Developer |
| Date | March 2026 |
| Input Document | Stage 1 — Discovery Meeting Transcript |
| Overall Verdict | FEASIBLE — Proceed to Stage 2 Design |

# 1. Introduction

A feasibility study evaluates whether a proposed software project is practical, affordable, technically achievable, and likely to succeed. This study examines the TastyBytes restaurant management system for Shiva Dhaba across five dimensions: Technical, Economic, Operational, Schedule, and Legal/Ethical.

Each section concludes with a verdict. The overall project verdict follows the individual assessments.

# 2. Technical Feasibility

Technical feasibility asks: Do we have the technology and skills to build this system?

## 2.1 Technology Stack Assessment

| Component | Build 1 (Supabase) | Build 2 (Spring Boot) |
| --- | --- | --- |
| Frontend | React + Tailwind CSS (TypeScript) | Same React frontend, API calls updated |
| Backend | Supabase + Edge Functions | Java Spring Boot REST API |
| Database | Supabase PostgreSQL | MySQL |
| Auth | Supabase Auth + JWT claims | JWT + Spring Security |
| Real-time | Supabase Realtime (orders) | WebSocket/STOMP (orders) |
| Support Chat | Netlify Functions + Socket.IO | Spring Boot + Socket.IO |
| Payments | Razorpay via Edge Function | Razorpay via Spring Boot controller |
| Hosting | Netlify (frontend) | VPS (backend) + Netlify (frontend) |

## 2.2 Technical Risk Assessment

| Risk | Level | Mitigation |
| --- | --- | --- |
| Real-time order updates latency | Low | Supabase Realtime tested and confirmed working on Netlify in existing codebase |
| Razorpay payment integration | Medium | Existing credentials available; move to Edge Function/Spring Boot controller to fix broken localhost dependency |
| QR code scanning on old devices | Medium | Web-based QR scan requires modern browser; fallback helper ordering flow handles older customers |
| Kitchen tablet performance | Low | Existing Android tablet confirmed available; lightweight kitchen UI designed for low-spec hardware |
| Data migration from existing schema | High | Schema health score 38/100 — full redesign required; migration scripts needed for existing order and customer data |
| Spring Boot for Build 2 | Medium | Developer actively learning; AI-assisted development with human review mitigates skill gap |

✅  TECHNICAL VERDICT: FEASIBLE

# 3. Economic Feasibility

Economic feasibility asks: Is the project financially justified? Will benefits outweigh costs?

## 3.1 Cost Estimate

| Cost Item | Build 1 (₹) | Build 2 (₹) |
| --- | --- | --- |
| Development (time-based estimate) | 0* | 0* |
| Supabase Pro Plan (monthly) | 2,500/mo | Nil |
| Netlify Pro Plan (monthly) | 1,500/mo | 1,500/mo |
| VPS Hosting — Backend (monthly) | Nil | 2,000/mo |
| MySQL cloud instance (monthly) | Nil | 1,200/mo |
| Razorpay transaction fee | 2% per txn | 2% per txn |
| Domain and SSL | 800/yr | 800/yr |
| Kitchen tablet (one-time) | 8,000 | 8,000 |

* Development cost is ₹0 as this is being built by the developer as a portfolio and learning project.

## 3.2 Benefit Estimate

Based on the discovery meeting, Shiva Dhaba experiences quantifiable losses without this system:

| Benefit | Estimated Value |
| --- | --- |
| Reduction in order errors / refunds | ~₹4,000–6,000/month saved |
| Billing accuracy (no undercharging) | ~₹2,000–3,000/month recovered |
| Admin time savings (manual reconciliation) | ~5 hours/week freed |
| Customer retention from digital experience | Estimated 10–15% increase in repeat visits |
| Festival/birthday coupon-driven revenue | Incremental — difficult to quantify pre-launch |

✅  ECONOMIC VERDICT: FEASIBLE — ROI within 3 months

# 4. Operational Feasibility

Operational feasibility asks: Will staff and customers actually use this system? Are there organisational barriers?

## 4.1 Stakeholder Readiness

| Stakeholder | Tech Comfort | Resistance Risk | Mitigation Strategy |
| --- | --- | --- | --- |
| Ramesh Gupta (Admin) | Medium | Low | He initiated the project. Primary motivator is reducing losses and gaining visibility. |
| Suresh (Counter Staff) | Medium | Medium | Billing system replaces manual calculator. Training session + parallel running period. |
| Kitchen Staff (5) | Low | High | Simple, large-font kitchen display. No typing required — status update via single button. |
| Helper Staff (2–3) | Very Low | High | Dedicated helper screen with one button only. Minimal interface. No login complexity. |
| Customers (Dine-in) | Variable | Low | QR ordering is optional. Paper menu + helper ordering preserved as fallback. |

✅  OPERATIONAL VERDICT: FEASIBLE — with training plan and parallel running

# 5. Schedule Feasibility

Schedule feasibility asks: Can this be delivered within an acceptable timeframe?

## 5.1 Proposed Timeline — Build 1 (Supabase Refactor)

| Phase | Deliverable | Duration |
| --- | --- | --- |
| Stage 1 | Discovery, Feasibility, Personas, PRD, Charter | Complete — March 2026 |
| Stage 2 | Schema design, API contracts, architecture diagram | Days 1–3 |
| Stage 3 | Database migration, RLS, Edge Functions, frontend updates | Days 4–10 |
| Stage 4 | Unit tests, integration tests, UAT with Ramesh | Days 11–13 |
| Stage 5 | Production deployment, staff training, parallel running | Days 14–16 |
| Stage 6 | Monitoring, bug fixes, handover documentation | Days 17–21 |

Build 2 (Spring Boot) follows after Build 1 is stable. It is primarily a learning and portfolio exercise and carries a separate timeline.

✅  SCHEDULE VERDICT: FEASIBLE — 21-day Build 1 target is achievable

# 6. Legal and Ethical Feasibility

Legal feasibility asks: Does this project comply with relevant laws, regulations, and ethical standards?

| Legal / Ethical Area | Status | Detail |
| --- | --- | --- |
| Customer PII storage (DPDP Act 2023) | ⚠️ Action Required | Names, phones, emails stored. Must implement data minimisation and deletion policy per India's Digital Personal Data Protection Act 2023. |
| Payment data security (PCI-DSS) | ✅ Compliant | Razorpay handles card data; system never stores raw card numbers. PCI-DSS compliance delegated to Razorpay. |
| GST invoice compliance | ✅ Compliant | 18% GST (9% CGST + 9% SGST) calculated automatically. GSTIN display on invoice required — to be provided by client. |
| Data retention policy | ⚠️ Action Required | Audit log and order data retention period must be defined. Recommended: 7 years for financial records per Income Tax Act. |
| Staff data (salary, attendance) | ✅ Low Risk | Internal use only. Not shared externally. Password-protected admin access required. |
| Open source licences | ✅ Compliant | React, Supabase, Spring Boot — all permissive licences (MIT, Apache 2.0). No GPL conflicts. |
| Accessibility | ✅ Good Practice | Customer QR ordering interface to meet WCAG 2.1 AA minimum contrast and touch target standards. |

✅  LEGAL VERDICT: FEASIBLE — Two action items to be addressed in Stage 2

# 7. Overall Feasibility Verdict

| Feasibility Type | Verdict | Key Condition |
| --- | --- | --- |
| Technical | ✅ Feasible | Data migration from schema 38/100 — risk managed |
| Economic | ✅ Feasible | ROI within 3 months; ongoing cost under ₹5,000/month |
| Operational | ✅ Feasible | Kitchen/helper UI must be maximally simplified |
| Schedule | ✅ Feasible | Build 1 in 21 days; Build 2 as follow-on |
| Legal / Ethical | ✅ Feasible | DPDP Act compliance and data retention policy required |

OVERALL VERDICT:  PROJECT IS FEASIBLE — APPROVED TO PROCEED TO STAGE 2