TASTYBYTES

Restaurant Management System

Stage 1  —  Project Charter

This document formally authorises the TastyBytes project and defines its scope, objectives, stakeholders, and governance.

| Project Name | TastyBytes — Shiva Dhaba Restaurant Management System |
| --- | --- |
| Project Sponsor | Ramesh Gupta, Owner, Shiva Dhaba, Ghaziabad |
| Project Manager / Developer | Aakash Jangid, Software Developer |
| Date Authorised | March 2026 |
| Project Purpose | To replace the paper-based order management system at Shiva Dhaba with a digital system that eliminates order errors, automates billing, and provides the owner with real-time business visibility. |
| Scope Summary | Build 1: Supabase serverless refactor of existing React frontend — fixing all 11 broken features, rebuilding the database schema, implementing proper authentication and RLS. Build 2: Full Spring Boot + MySQL traditional server rebuild with the same frontend. Both builds serve Customer, Kitchen, Counter, Helper Staff, and Admin roles. |
| Out of Scope | Inventory management, shift scheduling, performance reviews, multi-location support, delivery integrations, native mobile application. |
| Success Criteria | Zero lost orders for 4 consecutive weeks. Billing error rate below 1%. Admin can view daily revenue in under 30 seconds on phone. All staff operating without paper fallback by week 3 post-launch. |
| Timeline | Build 1: 21 days from Stage 2 completion. Build 2: Following Build 1 stabilisation. Both builds follow full SDLC: Stage 1 (Requirements) → Stage 2 (Design) → Stage 3 (Development) → Stage 4 (Testing) → Stage 5 (Deployment) → Stage 6 (Maintenance). |

Stakeholders

| Stakeholder | Role | Interest in Project |
| --- | --- | --- |
| Ramesh Gupta | Sponsor / Admin | Eliminate order losses, gain business visibility, reduce stress |
| Suresh Kumar | Counter Staff | Faster, error-free billing process |
| Kitchen Staff (5) | Kitchen Users | Clear, instant order communication from front of house |
| Helper Staff (2–3) | Delivery Users | Know which table to deliver to without confusion |
| Customers | End Users | Fast, convenient ordering and accurate billing |
| Aakash Jangid | Developer | Build production-quality portfolio project demonstrating SDLC mastery |

Risks and Mitigations

| Risk | Level | Mitigation |
| --- | --- | --- |
| Staff resistance to digital system | Medium | Parallel running period; maximally simple UI for kitchen and helper roles |
| Schema migration data loss | High | Full database backup before migration; migration scripts tested on copy first |
| Razorpay credentials exposed in git history | High | Rotate credentials immediately (P0 action — independent of SDLC) |
| Single developer — no backup resource | Medium | AI-assisted development; modular build so partial delivery is possible |
| Kitchen tablet hardware failure | Low | System works on any Android browser; backup device plan with Ramesh |

Authorisation

By signing this document, the project sponsor formally authorises the TastyBytes project to proceed to Stage 2 System Design.

| Role | Name | Signature / Status |
| --- | --- | --- |
| Project Sponsor | Ramesh Gupta | ✅ Verbally Approved |
| Developer | Aakash Jangid | ✅ Committed |